# Mid-Semester Project Plan — HiggsLens MVP

Mid-Semester MVP: Build and Validate the Core Experiment

# Goal

Deliver a working, understandable and defensible prototype quickly. The mid-semester scope should prove that the team understands the problem, can obtain and validate the official dataset, can fit the required model families, and can report a first honest comparison. Do not try to build every end-semester feature now.

# Deliverable definition

By the submission date, produce:

1. Executed notebook notebooks/01_midsem_mvp.ipynb with no failed cells.

2. Data overview: actual source, row count, label mapping, class balance, 28 inputs, and feature groups.

3. Three feature-set experiments: low-level only, high-level only, all 28 features.

4. At least Logistic Regression, XGBoost (with a clearly disclosed fallback only if XGBoost cannot be installed), and an MLP with batch normalization/dropout.

5. ROC-AUC, average precision, Brier score/calibration, accuracy as supplemental context, train time and prediction time where measured.

6. ROC/precision-recall/calibration plots and a model comparison table.

7. summary.md, results.csv, validation/test prediction exports and recorded run metadata.

8. A 4–6 page initial report or course-required equivalent and a short demo.

# Explicit data budget

Start with 250,000 events, which is within the assignment's recommended 250,000–1,000,000 starter range. If download, installation or hardware delays threaten the deadline, reduce the number only as a temporary diagnostic run; the submitted benchmark should meet the stated 250,000 lower bound if feasible. Record the source and number actually used. Do not label an under-sized emergency run as meeting the official budget.

The notebook reads the official UCI compressed stream for the requested row count. It may take time to download/decompress. Never commit the dataset to GitHub. If network access fails, download the official dataset from UCI manually and follow the local-file instructions in the notebook/README. Do not silently switch to an unverified smaller mirror.

# A day-by-day version (use relative days if deadlines differ)

## Day 1 — Understand and set up

Read docs/01_higgs_physics_for_beginners.md.

Create the GitHub repository and folder structure.

Open the notebook in Colab, check Python version, install dependencies, and verify that the source is accessible.

Record a first run's device, package versions, seed, source and data size.

Exit gate: imports run; no raw data or secrets are in Git.

## Day 2 — Data quality and EDA

Run schema checks: 29 columns when label is included, 28 features after target removal, both labels present, finite values, expected names.

Plot class count and a few low/high-level feature distributions.

Write a short explanation of what the plots establish and what they do not establish.

Exit gate: dataset and labels are understood; no preprocessing is fitted to test rows.

## Day 3 — Classical baselines

Fit Logistic Regression on the three feature groups using a StandardScaler fitted only on the training partition.

Fit XGBoost on the same three groups. Tree models may not need standardization for performance, but feature/model inputs and split remain comparable.

Record fit time and predicted scores.

Exit gate: six classical runs are recorded or a failed model is clearly documented; comparisons use consistent partitions.

## Day 4 — Neural baseline

Fit the specified compact MLP on low-level features and all features. Scaling is fitted on training rows only.

Use a fixed seed, a fixed epoch/batch configuration and a reasonable early stop/time budget if implemented.

Save model scores for validation and test.

Exit gate: at least the low-level and all-feature MLP runs finish and probabilities are finite.

## Day 5 — Evaluation and interpretation

Review ROC-AUC and average precision, calibration and Brier score, training cost and inference cost.

Select candidates using validation performance rather than repeatedly choosing based on test results.

For the MVP, use one prespecified operating objective (for example, target 80% signal efficiency) and choose the threshold on validation labels/scores. Report background rejection on test with that threshold unchanged.

Inspect permutation importance for one strong classical model only if runtime permits.

Exit gate: tables/plots can be regenerated from saved outputs.

## Day 6 — Report and demo

Write problem, dataset, methods, split, results, limitations and conclusion.

Build a short demo: problem → dataset → experiment → metrics → lesson → limitation.

Verify that every reported number appears in results.csv/metadata or can be recalculated.

Exit gate: all output files match the report.

## Day 7 — Buffer and viva practice

Re-run all notebook cells from a clean runtime.

Check links, filenames, output ZIP and app artifacts.

Practice explaining false positives, false negatives, overfitting, why the test set is held out, why the model cannot prove a discovery, and why Higgs-generated mass is not the source of most proton mass.

# The 2-hour emergency path

1. 0–10 min: open the notebook, read intro Markdown, run imports.

2. 10–25 min: load 250k official rows and run integrity checks.

3. 25–70 min: run the classical baselines.

4. 70–100 min: run the MLP.

5. 100–115 min: inspect metrics and plots.

6. 115–120 min: download outputs and record any unfinished work.

This is only a rush plan. If all models cannot finish in the window, do not fake scores or conceal the unfinished models; present the baseline that genuinely completed and state what remains.

# What to say in the mid-sem report

“We are constructing a reproducible simulated HIGGS event-classification benchmark. The first phase evaluates Logistic Regression, XGBoost and an MLP across low-level, physicist-derived and combined features on a documented subset. The aim is to measure the performance/compute trade-off and establish whether a model is suitable for further study. Results are preliminary and are not a real-data discovery claim.”

# What to defer until after mid-sem

Full 11-million-row experiments.

Multi-seed or bootstrap uncertainty studies.

Additional hyperparameter search.

Advanced feature attribution such as SHAP.

Authentication, deployment, cloud storage, user accounts or live detector feeds.

Any “discovery significance” claim.

# Mid-sem acceptance checklist

☐ Meets the dataset budget or clearly documents the blocker and actual smaller run.

☐ Contains low-level, high-level and all-feature comparisons.

☐ Includes Logistic Regression, XGBoost, MLP; fallback if used is identified.

☐ Train/validation/test logic is documented and seed is fixed.

☐ Preprocessing uses training data only.

☐ Metrics and plots are generated by code.

☐ Model selection is based on validation, not test.

☐ Scientific and compute limitations are explicit.

☐ Team can explain the notebook rather than merely display it.